CyberSentinel

Threat Intelligence Dashboard

Project Plan

ITMS 548 - Cybersecurity Technologies

Illinois Institute of Technology

April 16, 2026

Team Members:

Dennis Oseitutu - Project Lead & Lead Developer

Akinyemi Aremu - Security Researcher

William Smith - Network Security Specialist

# 1. Executive Summary

CyberSentinel is an open-source intelligent threat intelligence dashboard designed to aggregate, analyze, and visualize cybersecurity threats in real-time. The application integrates data from four major cybersecurity APIs to provide comprehensive security monitoring capabilities for organizations and security professionals.

Project Objectives:

- Develop a fully functional Python-based GUI application for threat intelligence monitoring

- Integrate at least four distinct cybersecurity data sources (NVD, AbuseIPDB, VirusTotal, AlienVault OTX)

- Implement comprehensive data analysis with visualizations and actionable insights

- Deliver production-ready open-source software with complete documentation

- Maintain professional project management standards throughout development

# 2. Project Timeline

Start Date: April 12, 2026

End Date: April 28, 2026

Total Duration: 16 days

| Phase | Tasks | Timeline | Owner |
| --- | --- | --- | --- |
| Phase 1 | Project Planning & Documentation | Apr 12-15 (3 days) | Dennis, Yemi, Will |
| Phase 2 | Core Application Development | Apr 18-20 (3 days) | Dennis, Yemi, Will |
| Phase 3 | API Integration | Apr 21-23 (3 days) | Dennis, Will |
| Phase 4 | Data Analysis & Visualization | Apr 24-25 (2 days) | Dennis, Yemi |
| Phase 5 | Testing & Documentation | Apr 26-27 (2 days) | All Team |
| Phase 6 | Final Review & Submission | Apr 28 (1 day) | All Team |

# 3. Detailed Task Breakdown

## 3.1 Phase 1: Project Planning & Documentation (Apr 12-15)

- Create comprehensive project plan document

- Develop risk management plan with mitigation strategies

- Initialize earned value tracking sheet

- Establish project management plan and communication protocols

- Set up GitHub repository with proper structure and README

- Define application architecture and technology stack

## 3.2 Phase 2: Core Application Development (Apr 18-20)

- Design and implement GUI framework using Tkinter

- Create main dashboard interface with navigation

- Develop database schema using SQLite for local data storage

- Implement configuration management system

- Build logging and error handling framework

## 3.3 Phase 3: API Integration (Apr 21-23)

- Integrate National Vulnerability Database (NVD) API for CVE data

- Integrate AbuseIPDB API for IP reputation checking

- Integrate VirusTotal API for file/URL scanning capabilities

- Integrate AlienVault OTX API for threat intelligence feeds

- Implement API rate limiting and error handling

- Create data normalization layer for consistent processing

## 3.4 Phase 4: Data Analysis & Visualization (Apr 24-25)

- Implement vulnerability trend analysis algorithms

- Develop threat scoring and risk assessment engine

- Create data visualizations using Matplotlib (charts, graphs, heatmaps)

- Build comprehensive reporting module

- Implement real-time dashboard updates

## 3.5 Phase 5: Testing & Documentation (Apr 26-27)

- Perform comprehensive functional testing

- Conduct integration testing for all API connections

- Create test document showing requirements verification

- Write comprehensive user documentation and installation guide

- Document code with inline comments and docstrings

- Update GitHub repository with final code and documentation

## 3.6 Phase 6: Final Review & Submission (Apr 28)

- Final application testing and bug fixes

- Review all deliverables against rubric criteria

- Update earned value sheet with final metrics

- Prepare submission package with all required documents

- Submit project before 11:59 PM deadline

# 4. Roles and Responsibilities

## 4.1 Dennis Osei Tutu - Project Lead and Developer

## Overall project management and coordination

- Lead application development and architecture design

- GUI implementation and user experience design

- API integration and data processing

- Documentation and testing oversight

- GitHub repository management

## 4.2 Akinyemi Aremu - Security Researcher and Developer

- Security analysis and vulnerability research

- Threat intelligence data validation

- Data analysis algorithm development

- Documentation review and quality assurance

## 4.3 William Smith - Network Security Specialist and Developer

- Network security analysis and monitoring

- API security and authentication implementation

- Integration testing and validation

- Technical documentation support

# 5. Key Milestones

| Milestone | Target Date |
| --- | --- |
| M1: All planning documents completed | April 17, 2026 |
| M2: Functional GUI framework completed | April 20, 2026 |
| M3: All four APIs successfully integrated | April 23, 2026 |
| M4: Data analysis and visualizations completed | April 25, 2026 |
| M5: Testing and documentation completed | April 27, 2026 |
| M6: Project submission | April 28, 2026 |

# 6. Project Deliverables

## 6.1 Documentation Deliverables

- Project Plan (this document)

- Risk Management Plan

- Earned Value Sheet

- Project Management Plan

- Test Document with requirements verification

- User Documentation and Installation Guide

## 6.2 Technical Deliverables

- CyberSentinel Application with full GUI

- Integration with 4 cybersecurity APIs

- Data analysis module with visualizations

- SQLite database for local data storage

- GitHub repository with complete source code

- README.md with project overview and setup instructions

# 7. Technology Stack

## 7.1 Programming Language

- Python 3.11+ (primary development language)

## 7.2 GUI Framework

- Tkinter (built-in Python GUI library)

- ttk themed widgets for modern interface

## 7.3 Data Sources & APIs

- National Vulnerability Database (NVD) API - CVE data

- AbuseIPDB API - IP reputation and abuse reporting

- VirusTotal API - File and URL security scanning

- AlienVault OTX API - Open threat intelligence feeds

## 7.4 Data Processing & Analysis

- pandas - Data manipulation and analysis

- Matplotlib - Data visualization and charting

- SQLite3 - Embedded database for local storage

- requests - HTTP library for API calls

## 7.5 Development Tools

- Git & GitHub - Version control and collaboration

- Visual Studio Code - Primary IDE

- pytest - Testing framework

# 8. Success Criteria

The project will be considered successful upon meeting the following criteria:

- Functional Application: CyberSentinel operates without critical bugs and provides all core features

- API Integration: All four data sources successfully integrated and returning data

- Data Analysis: Meaningful insights generated with clear visualizations

- User Interface: Intuitive GUI that is easy to navigate and use

- Documentation: Complete project documentation and code comments

- Testing: All requirements verified and test document completed

- GitHub Repository: Well-organized repository with professional README

- Rubric Alignment: Project meets or exceeds all rubric criteria for excellent (5/5) rating

# 9. Conclusion

CyberSentinel represents a comprehensive approach to threat intelligence aggregation and analysis. By leveraging multiple cybersecurity data sources and providing an intuitive interface, the application will serve as both a practical tool and a demonstration of advanced software development and cybersecurity principles. The project timeline is aggressive but achievable with focused effort and clear task prioritization. Success will be measured not only by meeting assignment requirements but also by delivering a tool that has real-world applicability in the cybersecurity field.