CyberSentinel

Threat Intelligence Dashboard

Risk Management Plan

ITMS 548 - Cybersecurity Technologies

Illinois Institute of Technology

April 28, 2026

Team Members:

Dennis Osei Tutu - Project Lead Developer

Akinyemi Aremu - Security Researcher & Developer

William Smith - Network Security Specialist & Developer

# 1. Introduction

This Risk Management Plan identifies potential risks that may impact the successful completion of the CyberSentinel Threat Intelligence Dashboard project. Each risk is assessed for probability and impact, with comprehensive mitigation, monitoring, and response strategies outlined to ensure project success within the 12-day timeline.

## 1.1 Risk Assessment Matrix

Risks are categorized using the following criteria:

Probability Scale:

- Low (1): 0-30% chance of occurrence

- Medium (2): 31-60% chance of occurrence

- High (3): 61-100% chance of occurrence

Impact Scale:

- Low (1): Minor impact, easily recoverable

- Medium (2): Moderate impact, requires significant effort to recover

- High (3): Severe impact, may jeopardize project success

Risk Score = Probability × Impact

# 2. Risk Register

## 2.1 Risk #1: API Rate Limiting and Access Restrictions

| Category | Technical |
| --- | --- |
| Description | Third-party APIs may impose rate limits or require authentication that could delay or prevent data retrieval during development and testing. |
| Probability | Medium (2) |
| Impact | High (3) |
| Risk Score | 6 (High) |

Mitigation Strategies:

- Register for API keys immediately on Day 1

- Implement caching mechanisms to reduce API call frequency

- Design application with rate limiting awareness (request throttling)

- Create mock data generators for testing without API calls

- Identify backup APIs for each data source category

Monitoring Plan:

- Test all API connections within first 24 hours

- Track daily API usage against rate limits

- Log all API errors and response codes

Response Plan:

- If rate limits hit: Switch to cached data or backup API

- If authentication fails: Contact API support immediately

- If API unavailable: Use pre-downloaded sample datasets for demonstration

## 2.2 Risk #2: Tight Project Timeline

| Category | Schedule |
| --- | --- |
| Description | A 12-day development window is aggressive for a full-featured application with multiple integrations, a GUI, and comprehensive documentation. |
| Probability | High (3) |
| Impact | High (3) |
| Risk Score | 9 (Critical) |

Mitigation Strategies:

- Prioritize MVP (Minimum Viable Product) features first

- Use agile daily sprints with clear deliverables

- Leverage existing libraries and frameworks (no custom implementations)

- Work extended hours if necessary (4-6 hours daily minimum)

- Build documentation incrementally alongside code

Monitoring Plan:

- Daily progress review against the earned value sheet

- Track milestone completion dates

- Identify scope creep immediately

Response Plan:

- If behind schedule: Cut non-essential features

- If significantly behind: Simplify the GUI to a basic functional interface

- Submit 1 day early (April 27) to avoid last-minute issues

## 2.3 Risk #3: Team Member Availability

| Category | Resource |
| --- | --- |
| Description | Team members may have limited availability due to other coursework, work commitments, or personal circumstances (e.g., hospitalization or deployment). |
| Probability | High (3) |
| Impact | Medium (2) |
| Risk Score | 6 (High) |

Mitigation Strategies:

- Primary developer (Dennis) takes ownership of all critical path tasks

- Assign clear, independent tasks that don't block other work

- Maintain comprehensive documentation so work can be handed off

- Use asynchronous communication (GitHub issues, comments)

- Plan for solo execution while welcoming team contributions

Monitoring Plan:

- Daily check-in via messaging

- Track task completion by individual team members

- Identify availability constraints early

Response Plan:

- If member unavailable: Reassign tasks to Dennis

- If extended absence: Continue with reduced scope if necessary

- Maintain team member names in documentation regardless of contribution level

## 2.4 Risk #4: Technical Integration Challenges

| Category | Technical |
| --- | --- |
| Description | Different API response formats, data structures, and authentication methods may create integration complexity and unexpected bugs. |
| Probability | Medium (2) |
| Impact | Medium (2) |
| Risk Score | 4 (Medium) |

Mitigation Strategies:

- Build modular API wrapper classes for each data source

- Implement comprehensive error handling and logging

- Create a data normalization layer to standardize different API formats

- Use well-documented APIs with Python SDK support when available

- Test each API integration independently before combining

Monitoring Plan:

- Unit test each API wrapper function

- Log all API responses for debugging

- Track integration bugs in GitHub issues

Response Plan:

- If API integration fails: Use alternative API or simulated data

- If data format incompatible: Implement custom parser

- If authentication complex: Simplify to basic API key authentication

## 2.5 Risk #5: Data Quality and Analysis Challenges

| Category | Quality |
| --- | --- |
| Description | Retrieved data may be incomplete, inconsistent, or require complex processing to generate meaningful insights. |
| Probability | Medium (2) |
| Impact | Medium (2) |
| Risk Score | 4 (Medium) |

Mitigation Strategies:

- Define clear, simple metrics for analysis (e.g., CVE counts, severity scores)

- Implement data validation and cleaning procedures

- Focus on visualizations over complex statistical analysis

- Use pandas for efficient data manipulation

- Prepare fallback analysis based on sample datasets

Monitoring Plan:

- Review data quality from each API during integration

- Validate analysis results make sense

- Test visualizations with real data early

Response Plan:

- If data insufficient: Augment with additional API calls or sources

- If analysis too complex: Simplify to basic trends and counts

- If visualizations unclear: Use standard chart types (bar, line, pie)

## 2.6 Risk #6: Software Dependencies and Environment Issues

| Category | Technical |
| --- | --- |
| Description | Python library version conflicts, OS compatibility issues, or missing dependencies may prevent application from running on different systems. |
| Probability | Low (1) |
| Impact | Medium (2) |
| Risk Score | 2 (Low) |

Mitigation Strategies:

- Use Python virtual environment (venv) for dependency isolation

- Create requirements.txt with exact version numbers

- Target Python 3.11 (widely available, stable)

- Use standard library when possible (Tkinter, sqlite3)

- Document installation steps clearly in README

Monitoring Plan:

- Test on clean Python environment regularly

- Verify all dependencies install correctly

- Test on both Windows and Linux if possible

Response Plan:

- If dependency conflict: Pin to compatible versions

- If library unavailable: Find alternative or implement custom solution

- If OS incompatibility: Document OS requirements clearly

# 3. Risk Summary Dashboard

| Risk | Probability | Impact | Score |
| --- | --- | --- | --- |
| Tight Project Timeline | 3 | 3 | 9 |
| API Rate Limiting | 2 | 3 | 6 |
| Team Member Availability | 3 | 2 | 6 |
| Technical Integration Challenges | 2 | 2 | 4 |
| Data Quality and Analysis | 2 | 2 | 4 |
| Software Dependencies | 1 | 2 | 2 |

Risk Priority:

- Critical (9): Tight Project Timeline - Requires daily monitoring

- High (6): API Rate Limiting, Team Availability - Active mitigation needed

- Medium (4): Technical Integration, Data Quality - Standard precautions

- Low (2): Software Dependencies - Minimal concern

# 4. Conclusion

This Risk Management Plan provides a comprehensive framework for identifying, assessing, and mitigating potential risks throughout the CyberSentinel project lifecycle. The primary risk driver is the aggressive 12-day timeline, which requires proactive daily monitoring and agile response strategies. By implementing the outlined mitigation strategies and maintaining vigilant monitoring, the project team can navigate these challenges successfully and deliver a high-quality threat intelligence dashboard that meets all assignment requirements.

This plan will be reviewed and updated as needed throughout the project duration, with particular attention to emerging risks or changes in team availability.